## Vivek Reddy Chereddy
Time Sheets
Name: Vivek Reddy Chereddy
Week | Sprint | Date | Day | Ticket | Tasks | Hour spent (hour)
Week 2 | Sprint 0 | 2026-07-20 | Mon | S0-01 | Team kickoff meeting; confirmed roles and Scrum Master responsibility | 2
|  | 2026-07-21 | Tue | S0-02 | Drafted Project Charter — stakeholders and governance structure sections | 4
|  | 2026-07-22 | Wed | S0-03 | Introductory meeting with Product Owner (MutualHub) and Academic Supervisor | 1.5
|  | 2026-07-23 | Thu | S0-04 | Drafted Product Backlog structure and mapped functional requirements (FR1-FR11) | 4
|  | 2026-07-24 | Fri | S0-05 | Researched Azure subscription options (student vs education tier) for cost planning | 3
Week 3 |  | 2026-07-27 | Mon | S0-06 | Facilitated backlog grooming session with the team | 2
|  | 2026-07-28 | Tue | S0-07 | Finalised Project Charter governance, communication and escalation sections | 3
|  | 2026-07-29 | Wed | S0-08 | Researched agentic AI architecture patterns for the lending platform | 3
|  | 2026-07-30 | Thu | S0-09 | Prepared Sprint 1 planning materials and capacity/velocity model | 2
|  | 2026-07-31 | Fri | S0-10 | Facilitated Sprint 0 wrap-up and led Sprint 1 planning session | 2
|  | Total hour spent in Sprint 0 |  |  |  | 26.5
Week 4 | Sprint 1
Week 5
|  | Total hour spent in Sprint 1 |  |  |  | 0
Week 6 | Sprint 2
Week 7
|  | Total hour spent in Sprint 2 |  |  |  | 0
Week 8 | Sprint 3
Week 9
|  | Total hour spent in Sprint 3 |  |  |  | 0
Week 10 | Sprint 4
Week 11
|  | Total hour spent in Sprint 4 |  |  |  | 0
Week 12 | Sprint 5
Week 13
|  | Total hour spent in Sprint 5 |  |  |  | 0

## Parv Ashokbhai Patel
Time Sheets
Name: Parv Ashokbhai Patel
Week | Sprint | Date | Day | Ticket | Tasks | Hour spent (hour)
Week 2 | Sprint 0 | 2026-07-20 | Mon | S0-01 | Team kickoff meeting | 2
|  | 2026-07-21 | Tue | S0-02 | Researched FastAPI vs Django for the backend service | 3
|  | 2026-07-22 | Wed | S0-03 | Researched PostgreSQL with pgvector for config storage and RAG | 3
|  | 2026-07-23 | Thu | S0-04 | Drafted initial backend data model (banks, products, applications) | 4
|  | 2026-07-24 | Fri | S0-05 | Researched Azure Database for PostgreSQL Flexible Server pricing tiers | 2
Week 3 |  | 2026-07-27 | Mon | S0-06 | Attended backlog grooming session | 2
|  | 2026-07-28 | Tue | S0-07 | Researched API design patterns for a multi-tenant, config-driven platform | 3
|  | 2026-07-29 | Wed | S0-08 | Set up local FastAPI project skeleton | 3
|  | 2026-07-30 | Thu | S0-09 | Researched core banking integration adapter patterns (FR7) | 3
|  | 2026-07-31 | Fri | S0-10 | Attended Sprint 1 planning session | 2
|  | Total hour spent in Sprint 0 |  |  |  | 27
Week 4 | Sprint 1
Week 5
|  | Total hour spent in Sprint 1 |  |  |  | 0
Week 6 | Sprint 2
Week 7
|  | Total hour spent in Sprint 2 |  |  |  | 0
Week 8 | Sprint 3
Week 9
|  | Total hour spent in Sprint 3 |  |  |  | 0
Week 10 | Sprint 4
Week 11
|  | Total hour spent in Sprint 4 |  |  |  | 0
Week 12 | Sprint 5
Week 13
|  | Total hour spent in Sprint 5 |  |  |  | 0

## Shivasainath R Kaluvala
Time Sheets
Name: Shivasainath R Kaluvala
Week | Sprint | Date | Day | Ticket | Tasks | Hour spent (hour)
Week 2 | Sprint 0 | 2026-07-20 | Mon | S0-01 | Team kickoff meeting | 2
|  | 2026-07-21 | Tue | S0-02 | Researched agent orchestration frameworks (LangGraph vs Semantic Kernel vs Azure AI Foundry Agent Service) | 4
|  | 2026-07-22 | Wed | S0-03 | Researched open-source LLMs for local development (Llama 3.1, Phi-4, Mistral, Qwen 2.5) | 3
|  | 2026-07-23 | Thu | S0-04 | Set up Ollama locally and test-ran candidate models | 3
|  | 2026-07-24 | Fri | S0-05 | Researched Azure OpenAI model catalogue and pricing (GPT-4o vs GPT-4o-mini) | 2
Week 3 |  | 2026-07-27 | Mon | S0-06 | Attended backlog grooming session | 2
|  | 2026-07-28 | Tue | S0-07 | Prototyped a minimal LangGraph agent graph | 4
|  | 2026-07-29 | Wed | S0-08 | Researched RAG approaches (pgvector vs Azure AI Search) for lending policy documents | 3
|  | 2026-07-30 | Thu | S0-09 | Researched AI safety/guardrails options (Azure AI Content Safety) | 2
|  | 2026-07-31 | Fri | S0-10 | Attended Sprint 1 planning session | 2
|  | Total hour spent in Sprint 0 |  |  |  | 27
Week 4 | Sprint 1
Week 5
|  | Total hour spent in Sprint 1 |  |  |  | 0
Week 6 | Sprint 2
Week 7
|  | Total hour spent in Sprint 2 |  |  |  | 0
Week 8 | Sprint 3
Week 9
|  | Total hour spent in Sprint 3 |  |  |  | 0
Week 10 | Sprint 4
Week 11
|  | Total hour spent in Sprint 4 |  |  |  | 0
Week 12 | Sprint 5
Week 13
|  | Total hour spent in Sprint 5 |  |  |  | 0

## Prince Rajeshbhai Patel
Time Sheets
Name: Prince Rajeshbhai Patel
Week | Sprint | Date | Day | Ticket | Tasks | Hour spent (hour)
Week 2 | Sprint 0 | 2026-07-20 | Mon | S0-01 | Team kickoff meeting | 2
|  | 2026-07-21 | Tue | S0-02 | Researched Next.js architecture (App Router, server components, streaming) | 3
|  | 2026-07-22 | Wed | S0-03 | Researched chat UI patterns for conversational AI interfaces | 3
|  | 2026-07-23 | Thu | S0-04 | Drafted wireframes for Customer chat, Loan Officer portal and Admin portal | 4
|  | 2026-07-24 | Fri | S0-05 | Researched Azure Static Web Apps deployment for Next.js | 2
Week 3 |  | 2026-07-27 | Mon | S0-06 | Attended backlog grooming session | 2
|  | 2026-07-28 | Tue | S0-07 | Set up local Next.js project skeleton | 3
|  | 2026-07-29 | Wed | S0-08 | Researched component/design libraries (shadcn/ui, Tailwind CSS) | 3
|  | 2026-07-30 | Thu | S0-09 | Reviewed frontend design considerations for multi-tenant bank branding | 2
|  | 2026-07-31 | Fri | S0-10 | Attended Sprint 1 planning session | 2
|  | Total hour spent in Sprint 0 |  |  |  | 26
Week 4 | Sprint 1
Week 5
|  | Total hour spent in Sprint 1 |  |  |  | 0
Week 6 | Sprint 2
Week 7
|  | Total hour spent in Sprint 2 |  |  |  | 0
Week 8 | Sprint 3
Week 9
|  | Total hour spent in Sprint 3 |  |  |  | 0
Week 10 | Sprint 4
Week 11
|  | Total hour spent in Sprint 4 |  |  |  | 0
Week 12 | Sprint 5
Week 13
|  | Total hour spent in Sprint 5 |  |  |  | 0

## Kamesh Chakkaravarthi
Time Sheets
Name: Kamesh Chakkaravarthi
Week | Sprint | Date | Day | Ticket | Tasks | Hour spent (hour)
Week 2 | Sprint 0 | 2026-07-20 | Mon | S0-01 | Team kickoff meeting | 2
|  | 2026-07-21 | Tue | S0-02 | Researched Azure landing zone setup (resource groups, subscriptions) | 3
|  | 2026-07-22 | Wed | S0-03 | Researched Azure Container Apps vs AKS for hosting the platform | 3
|  | 2026-07-23 | Thu | S0-04 | Researched CI/CD options (GitHub Actions vs Azure DevOps) | 3
|  | 2026-07-24 | Fri | S0-05 | Researched Azure Key Vault, Entra ID and Azure AD B2C for security foundations | 3
Week 3 |  | 2026-07-27 | Mon | S0-06 | Attended backlog grooming session | 2
|  | 2026-07-28 | Tue | S0-07 | Drafted Infrastructure-as-Code (Bicep/Terraform) plan for the Dev environment | 4
|  | 2026-07-29 | Wed | S0-08 | Researched Azure cost-optimisation options (consumption tiers, scale-to-zero) | 3
|  | 2026-07-30 | Thu | S0-09 | Set up shared GitHub monorepo structure | 3
|  | 2026-07-31 | Fri | S0-10 | Attended Sprint 1 planning session | 2
|  | Total hour spent in Sprint 0 |  |  |  | 28
Week 4 | Sprint 1
Week 5
|  | Total hour spent in Sprint 1 |  |  |  | 0
Week 6 | Sprint 2
Week 7
|  | Total hour spent in Sprint 2 |  |  |  | 0
Week 8 | Sprint 3
Week 9
|  | Total hour spent in Sprint 3 |  |  |  | 0
Week 10 | Sprint 4
Week 11
|  | Total hour spent in Sprint 4 |  |  |  | 0
Week 12 | Sprint 5
Week 13
|  | Total hour spent in Sprint 5 |  |  |  | 0