## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As a System Administrator, I want to configure a bank's branding and required documents, so that the platform reflects that bank's identity without code changes. |  | High | 8 | To Do | Configuration is stored and takes effect for that bank without a code deployment; verified on at least one test bank. | FR1 ¦ Sprint: Sprint 1 ¦ Merged from: PB-01, PB-03
2 | As a System Administrator, I want to configure loan products, interest rates, lending policies and AI behaviour/prompts, so that the platform follows each bank's business rules. |  | High | 13 | To Do | Configuration is stored and takes effect for that bank without a code deployment; verified on at least one test bank. | FR1 ¦ Sprint: Sprint 1 ¦ Merged from: PB-02, PB-04
3 | As a Customer, I want the AI Broker to welcome me, understand my financial goals and recommend a suitable loan type, so that I know where to start. |  | High | 13 | To Do | Behaviour demoed end-to-end in a live chat session with a test customer profile; reviewed by the team. | FR2 ¦ Sprint: Sprint 1 ¦ Merged from: PB-05, PB-10
4 | As a Customer, I want to provide my information and complete my application through natural conversation instead of forms, so that the process is simple and user-friendly. |  | High | 13 | Backlog | Behaviour demoed end-to-end in a live chat session with a test customer profile; reviewed by the team. | FR2 ¦ Sprint: Product Backlog ¦ Merged from: PB-06, PB-09
5 | As a Customer, I want the AI Broker to explain financial terminology and keep asking questions until it has everything it needs, so that I understand the process and my application is complete. |  | Medium | 8 | Backlog | Behaviour demoed end-to-end in a live chat session with a test customer profile; reviewed by the team. | FR2 ¦ Sprint: Product Backlog ¦ Merged from: PB-07, PB-08
6 | As a Customer, I want to view the available loan products and their key details, so that I can understand which product suits my needs. |  | High | 13 | Backlog | Feature demoed for all listed loan product types; changes visible to the customer without a deployment. | FR3 ¦ Sprint: Product Backlog ¦ Merged from: PBI-11, PBI-12, PBI-13
7 | As a System Administrator, I want to add and configure new loan products, so that the platform can support additional products without major code changes. |  | Medium | 8 | Backlog | Feature demoed for all listed loan product types; changes visible to the customer without a deployment. | FR3 ¦ Sprint: Product Backlog ¦ Merged from: PBI-14
8 | As a System Administrator, I want to update or deactivate existing loan products, so that the products available to customers stay current. |  | Low | 5 | Backlog | Feature demoed for all listed loan product types; changes visible to the customer without a deployment. | FR3 ¦ Sprint: Product Backlog ¦ Merged from: PBI-15
9 | As a Customer, I want to provide my personal, contact, employment and income information through conversation, so that my financial profile is captured. |  | High | 8 | Backlog | Required fields are captured and persisted correctly for a full test application; unit-tested. | FR4 ¦ Sprint: Product Backlog ¦ Merged from: PBI-16, PBI-17
10 | As a Customer, I want to provide my expenses, liabilities, assets, loan purpose, amount and term, so that the platform has everything it needs to assess my application. |  | High | 13 | Backlog | Required fields are captured and persisted correctly for a full test application; unit-tested. | FR4 ¦ Sprint: Product Backlog ¦ Merged from: PBI-18, PBI-19
11 | As a Customer, I want the AI Broker to identify missing information and ask relevant follow-up questions, so that my application is complete before it proceeds. |  | Medium | 8 | Backlog | Required fields are captured and persisted correctly for a full test application; unit-tested. | FR4 ¦ Sprint: Product Backlog ¦ Merged from: PBI-20
12 | As a Customer, I want to upload my identification and financial supporting documents, so that my identity and financial position can be verified. |  | High | 13 | Backlog | Feature demoed with at least 3 real-format sample documents; extracted/flagged data verified manually. | FR5 ¦ Sprint: Product Backlog ¦ Merged from: PBI-21, PBI-22
13 | As an AI Document Agent, I want to analyse uploaded documents and extract relevant information, so that manual data entry is reduced. |  | High | 8 | Backlog | Feature demoed with at least 3 real-format sample documents; extracted/flagged data verified manually. | FR5 ¦ Sprint: Product Backlog ¦ Merged from: PBI-23
14 | As an AI Document Agent, I want to identify missing or incomplete documents, and as a Loan Officer, I want to review the uploaded documents and extracted data, so that everything is verified before assessment. |  | Medium | 8 | Backlog | Feature demoed with at least 3 real-format sample documents; extracted/flagged data verified manually. | FR5 ¦ Sprint: Product Backlog ¦ Merged from: PBI-24, PBI-25
15 | As an AI Financial Assessment Agent, I want to calculate the customer's borrowing capacity and Loan-to-Value Ratio, so that an appropriate loan amount and risk level can be determined. |  | High | 13 | Backlog | Calculation verified against at least 5 reference scenarios with known correct answers; unit-tested. | FR6 ¦ Sprint: Product Backlog ¦ Merged from: PBI-26, PBI-27
16 | As an AI Financial Assessment Agent, I want to calculate the Debt-to-Income Ratio and loan serviceability, so that the customer's ability to meet repayments can be assessed. |  | High | 13 | Backlog | Calculation verified against at least 5 reference scenarios with known correct answers; unit-tested. | FR6 ¦ Sprint: Product Backlog ¦ Merged from: PBI-28, PBI-29
17 | As a Customer, I want to see my estimated repayments, and as a Loan Officer, I want to view the full financial assessment results, so that both of us understand the numbers. |  | Medium | 8 | Backlog | Calculation verified against at least 5 reference scenarios with known correct answers; unit-tested. | FR6 ¦ Sprint: Product Backlog ¦ Merged from: PBI-30, PBI-31
18 | As a System Administrator, I want the platform to expose secure, authenticated REST APIs with bank-specific adapters, so that different core banking systems can connect without changing core platform code. |  | High | 13 | Backlog | Feature demoed against the mock/simulated core banking adapter; contract test passes. | FR7 ¦ Sprint: Product Backlog ¦ Merged from: PBI-51, PBI-54
19 | As a Loan Officer, I want a customer's existing accounts and loans retrieved from the core banking system, so that current commitments are included in the assessment rather than self-declared. |  | Medium | 13 | Backlog | Feature demoed against the mock/simulated core banking adapter; contract test passes. | FR7 ¦ Sprint: Product Backlog ¦ Merged from: PBI-52, PBI-59
20 | As a System Administrator, I want loan products and interest rates synchronised from the core banking system, so that quotes reflect current bank pricing. |  | Low | 8 | Backlog | Feature demoed against the mock/simulated core banking adapter; contract test passes. | FR7 ¦ Sprint: Product Backlog ¦ Merged from: PBI-53
21 | As a Customer, I want my completed application submitted to the core banking system with a trackable status, so that I know where it sits without contacting the bank. |  | High | 8 | Backlog | Feature demoed against the mock/simulated core banking adapter; contract test passes. | FR7 ¦ Sprint: Product Backlog ¦ Merged from: PBI-55, PBI-56
22 | As a Loan Officer, I want the bank's approval outcome received and recorded, with all integration activity logged, so that the platform reflects the final decision and failures can be traced. |  | Medium | 8 | Backlog | Feature demoed against the mock/simulated core banking adapter; contract test passes. | FR7 ¦ Sprint: Product Backlog ¦ Merged from: PBI-57, PBI-58
23 | As a Loan Officer, I want the AI to validate submitted customer information, so that errors are caught before I review the file. |  | High | 5 | Backlog | Feature demoed on at least 3 test applications covering different outcomes; results reviewed by the team. | FR8 ¦ Sprint: Product Backlog ¦ Merged from: PBI-41
24 | As a Loan Officer, I want the AI to review uploaded documents and extract key fields, so that declared values are cross-checked automatically. |  | Medium | 8 | Backlog | Feature demoed on at least 3 test applications covering different outcomes; results reviewed by the team. | FR8 ¦ Sprint: Product Backlog ¦ Merged from: PBI-43
25 | As a Customer, I want to be told in plain language what information is still missing, and as a Loan Officer, I want each lending rule shown pass/fail against its threshold, so that gaps and rule breaches are clear. |  | High | 8 | Backlog | Feature demoed on at least 3 test applications covering different outcomes; results reviewed by the team. | FR8 ¦ Sprint: Product Backlog ¦ Merged from: PBI-42, PBI-44
26 | As a Credit Manager, I want serviceability and borrowing capacity assessed from verified data with risks identified, rated and linked to evidence, so that I can judge materiality before reviewing. |  | High | 13 | Backlog | Feature demoed on at least 3 test applications covering different outcomes; results reviewed by the team. | FR8 ¦ Sprint: Product Backlog ¦ Merged from: PBI-45, PBI-46
27 | As a Loan Officer, I want a structured credit assessment summary generated, so that I can review a file in minutes instead of reading raw documents. |  | Medium | 5 | Backlog | Feature demoed on at least 3 test applications covering different outcomes; results reviewed by the team. | FR8 ¦ Sprint: Product Backlog ¦ Merged from: PBI-47
28 | As a Loan Officer, I want exactly one of the four recommendations with a stated rationale, and as a Credit Manager, I want to override it with mandatory justification, so that the outcome is unambiguous and the final decision rests with a human, with everything stored for audit. |  | High | 21 | Backlog | Feature demoed on at least 3 test applications covering different outcomes; results reviewed by the team. | FR8 ¦ Sprint: Product Backlog ¦ Merged from: PBI-48, PBI-49, PBI-50
29 | As a Loan Officer, I want to view a queue of applications, review the AI recommendation and see the supporting evidence, so that I can work through pending decisions efficiently. |  | High | 13 | Backlog | Feature demoed by a team member acting as Loan Officer on a test application; action is logged. | FR9 ¦ Sprint: Product Backlog ¦ Merged from: new
30 | As a Loan Officer, I want to override a recommendation with a reason, and approve or reject the application, so that a final decision is recorded. |  | High | 8 | Backlog | Feature demoed by a team member acting as Loan Officer on a test application; action is logged. | FR9 ¦ Sprint: Product Backlog ¦ Merged from: new
31 | As a Loan Officer, I want to request further information from the customer, so that incomplete applications are completed without me contacting them manually. |  | Medium | 5 | Backlog | Feature demoed by a team member acting as Loan Officer on a test application; action is logged. | FR9 ¦ Sprint: Product Backlog ¦ Merged from: new
32 | As a System Administrator, I want to manage user accounts/roles and configure integration settings and API credentials securely, so that access and connections to external systems are controlled. |  | High | 21 | Backlog | Feature available in the Admin Portal UI; change takes effect without a redeploy; access-controlled. | FR10 ¦ Sprint: Product Backlog ¦ Merged from: new
33 | As a System Administrator, I want to create, version and roll back AI prompt templates, so that I can safely change AI behaviour over time. |  | Low | 8 | Backlog | Feature available in the Admin Portal UI; change takes effect without a redeploy; access-controlled. | FR10 ¦ Sprint: Product Backlog ¦ Merged from: new
34 | As a Loan Officer, I want every AI recommendation to show its explanation, evidence, calculations, source and confidence level, so that I can trust and verify it. |  | High | 13 | Backlog | Feature verified present on 100% of test recommendations/actions; reviewed against FR11 requirements. | FR11 ¦ Sprint: Product Backlog ¦ Merged from: new
35 | As a System, I want every important action recorded to an append-only, tamper-evident audit log, so that the platform is fully auditable. |  | High | 13 | Backlog | Feature verified present on 100% of test recommendations/actions; reviewed against FR11 requirements. | FR11 ¦ Sprint: Product Backlog ¦ Merged from: new
36 | As a Compliance-minded stakeholder, I want to export the full audit trail for a specific application, so that it can be reviewed end to end. |  | Low | 5 | Backlog | Feature verified present on 100% of test recommendations/actions; reviewed against FR11 requirements. | FR11 ¦ Sprint: Product Backlog ¦ Merged from: new
37
38
39
40

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a System Administrator, I want to configure a bank's branding and required documents, so that the platform reflects that bank's identity without code changes. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As a System Administrator, I want to configure loan products, interest rates, lending policies and AI behaviour/prompts, so that the platform follows each bank's business rules. | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a Customer, I want the AI Broker to welcome me, understand my financial goals and recommend a suitable loan type, so that I know where to start. | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a Customer, I want to provide my information and complete my application through natural conversation instead of forms, so that the process is simple and user-friendly. | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a Customer, I want the AI Broker to explain financial terminology and keep asking questions until it has everything it needs, so that I understand the process and my application is complete. | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As a Customer, I want to view the available loan products and their key details, so that I can understand which product suits my needs. | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a System Administrator, I want to add and configure new loan products, so that the platform can support additional products without major code changes. | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a System Administrator, I want to update or deactivate existing loan products, so that the products available to customers stay current. | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a Customer, I want to provide my personal, contact, employment and income information through conversation, so that my financial profile is captured. | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As a Customer, I want to provide my expenses, liabilities, assets, loan purpose, amount and term, so that the platform has everything it needs to assess my application. | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As a Customer, I want the AI Broker to identify missing information and ask relevant follow-up questions, so that my application is complete before it proceeds. | #N/A | #N/A | #N/A | #N/A | #N/A
12 | As a Customer, I want to upload my identification and financial supporting documents, so that my identity and financial position can be verified. | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As an AI Document Agent, I want to analyse uploaded documents and extract relevant information, so that manual data entry is reduced. | #N/A | #N/A | #N/A | #N/A | #N/A
14 | As an AI Document Agent, I want to identify missing or incomplete documents, and as a Loan Officer, I want to review the uploaded documents and extracted data, so that everything is verified before assessment. | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As an AI Financial Assessment Agent, I want to calculate the customer's borrowing capacity and Loan-to-Value Ratio, so that an appropriate loan amount and risk level can be determined. | #N/A | #N/A | #N/A | #N/A | #N/A
16 | As an AI Financial Assessment Agent, I want to calculate the Debt-to-Income Ratio and loan serviceability, so that the customer's ability to meet repayments can be assessed. | #N/A | #N/A | #N/A | #N/A | #N/A
17 | As a Customer, I want to see my estimated repayments, and as a Loan Officer, I want to view the full financial assessment results, so that both of us understand the numbers. | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a System Administrator, I want the platform to expose secure, authenticated REST APIs with bank-specific adapters, so that different core banking systems can connect without changing core platform code. | #N/A | #N/A | #N/A | #N/A | #N/A
19 | As a Loan Officer, I want a customer's existing accounts and loans retrieved from the core banking system, so that current commitments are included in the assessment rather than self-declared. | #N/A | #N/A | #N/A | #N/A | #N/A
20 | As a System Administrator, I want loan products and interest rates synchronised from the core banking system, so that quotes reflect current bank pricing. | #N/A | #N/A | #N/A | #N/A | #N/A
21 | As a Customer, I want my completed application submitted to the core banking system with a trackable status, so that I know where it sits without contacting the bank. | #N/A | #N/A | #N/A | #N/A | #N/A
22 | As a Loan Officer, I want the bank's approval outcome received and recorded, with all integration activity logged, so that the platform reflects the final decision and failures can be traced. | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As a Loan Officer, I want the AI to validate submitted customer information, so that errors are caught before I review the file. | #N/A | #N/A | #N/A | #N/A | #N/A
24 | As a Loan Officer, I want the AI to review uploaded documents and extract key fields, so that declared values are cross-checked automatically. | #N/A | #N/A | #N/A | #N/A | #N/A
25 | As a Customer, I want to be told in plain language what information is still missing, and as a Loan Officer, I want each lending rule shown pass/fail against its threshold, so that gaps and rule breaches are clear. | #N/A | #N/A | #N/A | #N/A | #N/A